## Oct roadmap
Initiative |  | Description | Validation | Owner | Priority | Status | Product | Design | Dev- Frontend | Dev-Backend | Clarifications/Blockers | Need resolution from | Remarks | Resolution
AI review attempts Transcript + wrong attempted questions based generated flashcards | Core Learning outcomes | conceptual understanding | Success rate for second attempt: 78% | Lalithanjali | 0 | Todo |  |  |  |  | deprioritized
Micro learning with instant reinforcement | R&D |  |  | Sarthak | 0 | Discarded | 2025-09-05 |  |  |  | could be operational, possibly no tech involved
AI evaluation improvement | AI features improvements |  |  | Shreshth | 0 | Done
Changing to new portal for instructors | NIAT learning experience |  |  | Rohan | 0 | Done |  |  |  |  | mostly operational task, might have a small tech task
English product | English, Aptitude track |  |  | Lalithanjali | 0 | Done
Dynamic quiz at milestones (module quiz) | Core Learning outcomes | New MCQ Unit type which will have a dynamic quiz based on unattempted/wrongly attempted questions |  | Rohan | 1 | Discarded | 2025-09-05
Code playground revamp | Core Learning experience | Revamping the look and feel of the code playground for JS |  | Lalithanjali | 1 | Done | 2025-08-29
Subtitles for videos | Core Learning outcomes |  |  | Sarthak | 1 | Done
UX review action items | Core Learning experience | 1. Persistence- curriculum expansion 2. Persistence - schedule date 3. Holiday and exam integration into the calendar 4. entered input persistence 5. Auto-save rests code |  | Rohan | 1 | Done
AI tutor improvements | AI features improvements | - adding dependability in responses - Fixing experience action items - adding user level memory |  | Shreshth | 1 | Todo
Mind map v2 |  |  |  | Sarthak | 1 | Done
Daily Revision v2 | Core learning outcomes | Improving revision with a better pedagogical approach to improve revision effectiveness and engagement |  | Sarthak | 3 | Next month | 2025-09-04 |  |  |  | POC with Suraj. If done then will pick
Social highlighting |  | Reading materials, cheatsheets are long and not scanable; which is needed particularly during revision. Also, as a group, people will highlight most important point. Adds to the social signal that a certain concept is important and should be learnt | Secondary research done | Rohan | 2 | Discarded
Gamified Practice sessions | NIAT learning |  | Check if needed | Sarthak | 2 | Todo | Todo | Todo | Todo | Todo
Dark mode |  |  |  | Lalithanjali | 2 | Next month
Live Quiz gamification |  |  | Check if extrinsic motivators needed for Live Quiz | Lalithanjali | 3 | Todo
Spoken English and communication BOT |  | Helping the team with Communication BOT from PM POV |  | Lalithanjali |  | Done
AI tutor improvements |  |  |  | Sarthak | 2 | Done

## Sept roadmap
Initiative | Description | Validation | Owner | Priority | Status | Product | Design | Dev- Frontend | Dev-Backend | Clarifications/Blockers | Need resolution from | Remarks | Resolution
Session exploration bot - AI Tutor | Tutor at video session and cheatsheet that helps user explore more on the learning covered in the unit. |  | Anurag | 0 | Done | 2025-08-29 | 2025-09-02 | 2025-09-04 | 2025-09-04 | Design- 1st Draft by EOD. Frontend- This task can be started only after the Video unit revamp
n8n playground | Integrating n8n playground in platform |  | Anurag | 0 | Done | 2025-08-29 | 2025-09-03 |  | 2025-09-05 | Design- need more clarification from Anurag Frontend- can be started only after DB model task
NIAT ¦ Exams | Developing a new flow where students can view scheduled assessments in the Learning Portal. After completion, the results are synchronized with the backend, and the portal displays the results to the student. |  | Lalithanjali | 0 | Done | 2025-09-04 |  |  |  | ideated
Micro learning with instant reinforcement |  |  | Lalithanjali | 0 | Discarded | 2025-09-05 |  |  |  | Ideation with pedagogy team
NIAT¦ Feedback - Practice | Incorporating feedback even for practice sessions to track and evaluate the quality of mentors in class |  | Lalithanjali | 0 | Done | 2025-09-04
NIAT ¦ Chaptering the Videos |  |  | Lalithanjali | 1 | Done
Live Quiz v3 | Adding student report Adding question level timer |  | Rohan | 1 | Done
Social highlighting | Reading materials, cheatsheets are long and not scanable; which is needed particularly during revision. Also, as a group, people will highlight most important point. Adds to the social signal that a certain concept is important and should be learnt | Secondary research done: Medium, other long form blogs have this social highlighting | Rohan/Lalithanjali | 1 | Next month |  |  |  |  | Defined but not picked due to other urgent tasks
Guided coding |  |  | Anurag | 2 | Todo
AI tutor for cheatsheet | Solve any doubts instantly, encourage doubt asking by reducing friction Deep dive into a certain concept to encourage self exploratory learning |  | Lalithanjali | 2 | Done
Better review attempts Transcript + wrong attempted questions based generated flashcards | conceptual understanding | check the success rate in attempt 1 if 90-95% then no use if 70-80% then can do | Lalithanjali | 2 | Next month |  |  |  |  | deprioritized
All learning pages revamp | Revamping the look and feel of the navigation & video unit page across NIAT in sync with 10xiit 1. videos 2. nav bar 3. coding question - all types 4. mcqs 5. exams 6. cheatsheet |  | Lalithanjali | 3 | Next month | 2025-08-29 | 2025-09-02 | 2025-09-04 | 2025-09-04 | Check with Lokeshwar on status and pick after they have done the majority of the work
Daily Revision v2 | Improving revision with a better pedagogical approach to improve revision effectiveness and engagement |  | Anurag | 3 | Done | 2025-09-04 |  |  |  | POC with Suraj. If done then will pick
NIAT ¦ Monthly Feedback | Create a feedback loop that informs design and product decisions monthly. The monthly feedback loop will focus only on UX and flow improvements. |  |  |  | Discarded | 2025-09-04
Dynamic quiz at milestones (module quiz) | New MCQ Unit type which will have a dynamic quiz based on unattempted/wrongly attempted questions |  | Anurag | 3 | Next month | 2025-09-05
NIAT ¦ Feedback design improvement | Revamping the look and feel of the feedback system in NIAT to make it more relevant and reduce the no of clicks |  | Lalithanjali | 3 | Done | 2025-09-04
Code playground revamp | Revamping the look and feel of the code playground across NIAT in sync with 10xiit |  | Lalithanjali | 3 | Done | 2025-08-29 |  |  |  | Done for coding Q and web coding

## Aug roadmap
Initiative | Description | Timeline | Priority | Effort | Status |  | Clarifications/Blockers | Need resolution from | Remarks | Resolution
NIAT ¦ Better in class experience with schedule | - Giving a collapsed view of previous completed classes and next classes to reduce information overload - Auto focus and enlarging of current class card to reduce need for student to find current class manually and focus attention on just the class materials |  | 0 |  | Done | -
NIAT ¦ Profile trimming down | Reducing profile sections fields to necessary ones |  | 0 |  | Done | On track
Frontend evaluation - Questions | Question evaluation back integration |  | 0 | XL | Done | Delayed | question evaluation part to be done in Topin first |  | KV | Due to bandwidth constraints, have delegated to Topin tech team and waiting on their implementation
SQL evaluation | DB modelling interface and evaluation |  | 0 |  | Done | -
NIAT ¦ Announcements integration |  |  | 1 |  | Done | -
NIAT ¦ Exam integration | Integrating with Topin to have a well functioning Exam creation, attempting and result tracking and showing flow for all Exams. |  | 1 |  | Done | Delayed | Pending clarifications from Vijay/Kiran P
NIAT ¦ Help experience standardisation | - Enable AI tutor by default for NIAT - Load and enable mentor bot at all content types - Add AI tutor for MCQs, videos, cheatsheets |  | 1 |  | In progress | Delayed, will be partially done | Large scope, cannot be done in single roadmap
Prod error resolution | Streamline the process from error identification to resolution |  | 1 | M | Discarded | Not picked | Operational, not picked |  |  | Delayed due to lack of product bandwidth
NIAT ¦ Changing bookmarks, saved snippets to new design | Design standardization |  | 2 |  | Done | On track
Frontend evaluation - Project | Project evaluation |  | 2 | L | Todo | Delayed | Bandwidth, not urgent |  | Anurag

## New Initiatives
Themes | Initiative | Priority | Status | Why? | Data to check | DA remark
Learning - session | Session exploration bot | 1 | Done
Learning - Video | While watching video, user has doubts: Quick AI tutoring if student did not understand a particular part of a video | 1 | Done | Learning
Learning - Video | Before user watches video: Pre check to cut down video | 1 | Discarded
Learning - Reading | Social highlighting Part 1: highlighting Part 2: social Part 3: show at a single place | 1 | In progress | Reading materials, cheatsheets are long and not scanable; which is needed particularly during revision. Also, as a group, people will highlight most important point. Adds to the social signal that a certain concept is important and should be learnt | Secondary research done: Medium, other long form blogs have this social highlighting
Learning - Video | Improved hotspots: Ask learners to predict an outcome before playing a key clip | 1 | Backlog | engagement
Practice - MCQs | Better review attempts Transcript + wrong attempted questions based generated flashcards | 1 | In progress | conceptual understanding | check the success rate in attempt 1 if 90-95% then no use if 70-80% then can do
Practice - Coding | Write test case for coding question | 1 | Todo | Currently, expecting students only to pass testcases. But if we ask them to write testcases, they will think of input/output, all the exhaustive edge cases. It will specifically help improving edge cases identification among students | How many times do students miss edge cases and are unable to pass the last 1-2 testcases while running or submitting code?
Practice - Coding | Debug faulty code | 1 | Todo | - students don't know how to use debugger - students don't find any value in the debugger |  |  | idea: Find out the fault in the code with the help of debugger
Practice - Coding | Evaluator for web coding | 1 | In progress
Evaluation | Project evaluator | 1 | Todo
Internal enablement | n8n playground | 1 | In progress
Learning - Video | Alternative to long video and single set of mcqs: Micro learning with instant reinforcement | 1 | In progress | cognitive load / resistance to start
Learning - Reading | AI tutor for cheatsheet | 1 | In progress | Solve any doubts instantly, encourage doubt asking by reducing friction Deep dive into a certain concept to encourage self exploratory learning
Practice - MCQs | Dynamic practice: No predefined mcq practice questions. Dynamically picking questions from a pool each time based on user previous attempts, | 2 | Todo
Practice - Coding | Guided coding | 2 | Todo
Evaluation | Dynamic examinations | 2 | Todo | Similar to GRE format. Enables more accurate evaluations
Tooling | Allow content testing by building an A/B testing functionality into LP - curriculum team loads 3 versions of the same video, experimenting with teaching pedagogy, instructor, length of video, depth of explaination | 2 | Todo
Practice - MCQs | Confidence-weighted practice | 3 | Todo | Discourage guessing, gauge confidence on top of correctness. | How many are guessing? | Ask curriculum team to attempt 2-3 practices themselves Track their time Whoever doing significant in lesser time, could be guessing?
Tooling | Curriculum recommendation engine: Analyze learning content against collected interview intelligence (TR round data, industry job descriptions) and emerging tech trends to identify curriculum gaps and outdated modules. | 3 | Todo
Engagement/Extrinsic motivators | In platform+ off platform engagement: AI buddy with contextual motivations | 3 | Todo
| Daily Revision |  | In progress
| Dynamic quiz at milestones (module quiz) |  | Todo
Student facing Product Suite | AI Personalised Learning
Student facing Product Suite | AI Practice Pilot
Student facing Product Suite | AI Exam Feedback bot
Student facing Product Suite | AI Revision Pilot
Student facing Product Suite | AI Video Session Context Pilot
AI Creator Suite | AI Curriculum Designer
AI Creator Suite | AI News Curator (Personalised to a domain, individual)
AI Creator Suite | AI Feedbacks Cruncher
AI Creator Suite | AI Lesson Planner
AI Creator Suite | AI Content Generator
AI Creator Suite | AI ICP for Content Reviewer
Content Delivery & Ops suite | AI Recorded Content Quality checker
Content Delivery & Ops suite | AI Student Diagnostics Report Generator
NIAT on-ground feedback | Gamification: Add leaderboards across entire university for module quizzes

## Further
Theme | Initiative | Why this? | Action items
NIAT Learning | Improve practice session experience | - Students get a mcq/coding practice and they solve it online - Missing to capitalise on in person presence - No real time tracking of engagement and completion | - Learn more about the current practice experience - Find out optimal, scalable way
NIAT Learning | Automated project/exam evaluations wherever manual evaluation is happening | - Manual evaluations not scalable | - Find out what is being manually evaluated
NIAT Learning | AI Guided Group Discussions
Multiplier, Learning experience | 10-100 previous successful features - Adaptive - Revision - AI Tutor
AC/IN gamification systems | Incentivize course completion through social motivators - Pavan initiated - Gamification scope? | Increase course completion
Internal enablement | Evaluation Mechanism/content types for new courses - MySQL in Aug/Sept - Django in Sep/Oct
LMS | Tech - Simplifying configs - Removing unused/obsolete features (Guiding, Approach) - Building modular lms layer that can be repurposed for any program | - Ease scaling - Reduce possible errors in future by limiting options - Reduce TAT for new program launches - Current platform a collection of disjointed features, rather than a well thought out connected experience
Academy/Intensive experience | Academy/Intensive User experience - portal user experience design | - Disconnected experience - Improve learning efficiency, user engagement
CMS | Content visibility for University in order to create exams
Topin - AI futureproofing | Proctoring upgradation in exams/assessments | - Increase evaluation dependability through exams - Current systems are not dependable in current AI world
AI eval system | - End to end, reusable eval system in tech using which any AI feature can be evaluated dependably
CMS | Allow content testing by building an A/B testing functionality into LP | Different forms of content
New Initiative | Completely new adaptive, personalized learning platform | - Developments and improvements in current platform are limited by it's underlying structure - With all the new tools and technologies, can try a new platform that is entirely adaptive and personalized
Content Intelligence & Optimization | Skill Gap Analysis: Automatically analyze learning content against collected interview intelligence (TR round data, industry job descriptions and emerging tech trends) to identify curriculum gaps and outdated modules.
Extension: Generate recommendations for new content creation priorities based on market demand data
Content Performance Analytics: Track content engagement patterns against student outcomes to identify high-impact vs low-value learning materials.
Extension: Suggest content restructuring, merging, or elimination based on learning efficacy data
Assessment Calibration: Cross-validate assignment difficulty and interview success rates to ensure assessments accurately predict real-world performance.
Extension: Auto-adjust question complexity and weightage based on industry feedback loops
Intelligent Doubt Resolution: Deploy context-aware agents that understand student queries across multiple coding questions and provide relevant guidance.
Extension: Auto-escalate complex queries to appropriate mentors with full context and suggested solutions
IRS system | need to push this to relevant teams. Outcome: give a dependable indicator of student performance for internal use
NIAT ¦ Year - semester heirarchy addition | Currently hardcoded hence will work only upto 1st year
Knowledge graph based learning

## June-July 2025 roadmap
Initiative | Description | Can be planned? | Timeline | Priority | Effort | Status | Clarifications/Blockers | Need resolution from | Remarks | Resolution
NIAT LP v1 | 1. Show schedule specific to uni/section 2. Lock/unlock 3. Resources linking | Yes | 2025-06-13 | 0 | XL | Done | Waited for NIAT Apps team to implement Had to implement some part of theirs |  | Waited for NIAT Apps team to implement Had to implement some part of theirs
Adding SQL visualizer to code playground |  | Yes | 2025-06-20 | 0 | M | Done
Cloud IDE + Github Copilot POC |  | Yes | 2025-06-20 | 0 |  | Done |  |  | Delayed due to Refactoring task - to align topintech & LP backend engineering task
Gen AI course enabling n8n POC |  | Yes | 2025-06-20 | 0 |  | Done |  |  | Borrowed one backend dev for a week and did self hosting with two different options.
NIAT LP v2 | 1. Feedback 2. Profile | Yes | 2025-06-27 | 0 | S | Done
Cloud IDE + Github Copilot implementation |  | No | 2025-07-04 | 0 | M | In progress |  | Lavanya
SQL visualizer expansion | Supporting all the required keywords (100% coverage) | Yes | 2025-07-04 | 0 | XL | In progress | Currently at 70% |  | Delayed by a week due to single resource working on this. Resource is not frontend
Gen AI course enabling - Prompt evaluation | - Providing support for partial scoring | Yes | 2025-07-04 | 0 | L | Done | partial scoring is needed by July first week |  | Dependends on sourabh's availability or visualizer task might get delayed
Gen AI course enabling n8n integration and evaluation implementation |  | Yes | 2025-07-11 | 0 | L | Done |  |  | Delayed due to lack of tech resource
AI course enabling Google colab usage |  | Yes | 2025-07-11 | 1 | M | Blocked | Already using colab in DSML. Curriculum team checked. some things need to be added from tech
SQL evaluation | DB modelling interface and evaluation | Yes | 2025-07-18 | 1 | M | In progress |  |  | Delayed due to lack of backend resource and product bandwidth
LP UI/UX | Entire design system overhaul for NIAT | No | 2025-08-15 | 2 | XL | In progress | Need to decide scope | Anurag
LP onboarding experience | First time LP opening experience 1. Understand the existing 2. Create new flow | No |  | 3 | L | In progress | There is already an existing flow. Do we need to create a new onboarding flow? | Anurag
MCP server |  | Yes |  | 3 | L | Done | Taken up by Data team
Instructor/Mentor LP

## Roadmap (March - May)
Pod | Product | Core Metric / Direction of Work | Phases | Theme | Initiative | Why this? | Responsible Person | Supporting Person | Start Date (Dev) | End Date | Goal/Target | Prod Effort (P,Dev,Design) | Ops Effort (Content, Sales, Mktng, etc) | Priority | Stage | Remarks
| All | Independent problem solving Learning experience |  | AI Tutor | AI Tutor chat version | - To be released for NIAT which is not compatible with voice to voice mode - 16% less questions solved by AI tutor users as compared to control group in Intensive experiment - More in-progress questions (2% vs 1.5% normally) User Pain point: - Accessibility issue with voice to voice | Anurag |  | 2025-03-17 | 2025-03-28 | - Reduce in progress questions - Eliminate the 16% drop in questions solved | L | - | 1 | Done
| NIAT |  |  | NIAT Learning Experience | React Code in Tutorial | Enhanced practical learning experience for React concepts | Preethi/Lavanya |  | 2025-03-17 | 2025-03-28 | - Improve conceptual understanding in React | M | L | 4 | Done
| All | Independent problem solving Learning experience |  | AI Tutor | AI Tutor for IDE | Increase coverage of AI tutor - Budget approval | Anurag |  | 2025-03-31 | 2025-04-11 |  | M | - | 2 | Done
| NIAT | NIAT Learning experience |  | NIAT Learning Experience | Live Quiz for NIAT | - Too late to identify if students are struggling - Lectures are one-way - No data on engagement - Missed teaching opportunities | Anurag |  | 2025-03-31 | 2025-04-18 | - 80%+ students engaging in lectures - Real time data availability for instructors | L | L | 3 | Done | pooling to be discussed
| All | Cost reduction |  | AI Tutor | AI tutor cost reduction - Modular - Caching - Optimization |  | Lavanya/Rajesh |  | 2025-03-31 | 2025-04-11 | Reduce cost from 0.12$ per conversation to __ | L | - | 5 | Done
| All | Independent problem solving Learning experience |  | AI Tutor | AI Tutor question expansion | Increase coverage of AI tutor | Lavanya |  | 2025-04-14 | 2025-04-25 | Cover 80% of all coding (all types) questions | XL | - | 6 | Done
| All | Knowledge retention |  | Knowledge retention | Revision enhancements proactive | Improve usage and algorithm effectiveness Completion rate: 35% Used once: ~30-40% | Anurag |  | 2025-04-14 | 2025-04-25 | - 85%+ use it atleast once - 70%+ use it atleast 3 times - Started to completion rate 90%+ - algorithm parameters in ideal range | L | - | 8 | Done
| All | Independent problem solving Learning experience |  | AI Tutor | AI tutor Level 2 help | - 16% less questions solved by AI tutor users as compared to control group - More in-progress questions (2% vs 1.5% normally) User Pain point: - Absence of level 2 help (Level 1 help: overall guidance with indirect hints, level 2 help: actual help with direct hints/solution) | Anurag |  | 2025-04-14 | 2025-04-25 | - Reduce in progress questions - Eliminate the 16% drop in questions solved | L | - | 9 | Done
| All | NIAT Learning experience |  | NIAT Learning Experience | SQL Visualiser | Improved conceptual understanding of SQL query execution | Chanakya/Lavanya |  | 2025-04-14 | 2025-04-25 | - Reduction in SQL queries - Classroom Quiz, Daily Quiz performance | L | L | 15 | Done
| NIAT | NIAT Learning experience |  | NIAT Learning Experience | Personalized revision for NIAT remedial | POC: Revision week for NIAT Findings: | Anurag |  | 2025-04-28 | 2025-05-09 | - Improved Fortnight quiz performance - Increase practice completion % | L | - | 7 | Next roadmap
| All |  |  | AI futureproofing | prompt2ui integration | Integrate prompt2ui questions in frontend course | Anurag |  | 2025-04-28 | 2025-05-09 |  | L | L | 10 | Discarded
| All | Independent problem solving |  | AI futureproofing | GPT proof coding practice - Adding AI tutor flow that checks for AI influence and/or are harder to cheat on | Prevention against user cheating using AI tools Check if time to solve reduced after GPT | Anurag |  | 2025-05-12 | 2025-05-23 | Identify AI assisted question solves by students | M | S | 11 | Next roadmap
| NIAT | NIAT Learning experience |  | NIAT Learning Experience | Improve practice session experience | - Students get a mcq/coding practice and they solve it online - Missing to capitalise on in person presence - No real time tracking of engagement and completion | Anurag |  | 2025-05-12 | 2025-05-23 | - Track and increase engagement in practice sessions | L | S | 12 | Next roadmap
| All | Content loading efficiency |  | Internal tooling | Content generation and loading with bedrock | Automate content process | Anurag | Rajesh | 2025-05-12 | 2025-05-23 | Generate and load a complete MCQ practice with minimal manual work time saved errors avoided | L | S | 13 | Next roadmap
| NIAT |  |  | AI futureproofing | Feasibility check on integrating Github copilot with cloud IDE - check on ability to use Github Educator Program for all student accounts | AI led content and pedagogy | Preethi/Anurag |  | 2025-05-12 | 2025-05-23 |  | M | XL | 14 | Discarded
| All | Course completion % |  | Course completion % | Reduce the workload by making the course adaptive to user skill and competence: Adaptive MCQs | 85% Intensive users are unable to complete the eligiblity units for PF in given time due to: Pain point: - The course being too long and repetitive | Anurag |  | 2025-05-26 | 2025-06-06 | - Reduce median time to complete PF from 45 days to 40 days - Academy: - Increase in time course completion by | M | S | 16 | Next roadmap | on time completion unit completion time reduced
| All | Content coverage |  | Enabling new course | Evaluation Mechanism/content types for new courses: Typescript NextJS Redux System Design Machine learning |  | Anurag |  | APR | APR | - Seamless learning experience with new learning materials | XL | - | 17 | Done