## Content
Requirement | Status | Why this feature is needed | Requirement raised by | Effort | priority of the requirement | Comments | Expected Timeline | Delivery date
Need a unit in learning portal where we can have multiple types units init. MCQs (All types of MCQ formats) Coding (IDE coding, JS coding, HTML coding) | Done | For course exam it will be better to have all the exams in one unit * This will make the user feel that they have to complete one unit to get course completion certificate * We can use these kind of units to check if the candidate is theoritically and practically good with one unit | Chanakya |  | 0
Course versioning based certification | Discarded | We need to update the criteria of course completion to get quality candidates | Chanakya |  | 1 | to be raised to retention
Coding IDE exam feature | Done | Filtering of quality cadidates without IDE exam feature, is not possible | Chanakya |  | 0
Review attempts card disable | Discarded | For course exams, we are not enabling review attempts. If we does it reveals all the questions to the users and they can copy more easily and we need to generate more pool in a regular basis. Currently we dont have any configuration to hide / disable the review attempts button. - We need a script to disable / hide the review attempts button. - We need a key where if the key value is true Pass/ fail should be enable and of it is false then user should not able to view pass/ fail. He should only get the score | Kavya |  | 1 | Raised a seperate task for addressing the issue hence discarding this
Need a jupyter script for updating test_cases for IDE based coding questions | Done | As of now we are updating the test_cases with the help of tech team, it's difficult to reachout them when ever there is requirement. If they provide a script for us we will update without any dependency of other teams | Swami |  | 0 |  |  | 2023-09-04
Change completion criteria of Tutorials | Done | Recently we changed 4 Reading materials into Tutorials along with MCQs in BETA. In actual after completion of reading material, the unit will be marked as completed, but in this tutorial when I click the continue button before the last step, without completing the step it will be marked as completed |  |  | 0
To get and error/ warning if we delete the content if it is already exists in multiple places | In sprint | while trying to delete a unit it should shown error that questions in that unit are linked to some other units as well. So, if it throws this type of error that should help full us for not loosing existing data. If knowing or unknowingly any one trying to delete it will giving clear clarity. | Vijay | 1 | 1 | Redoing this as requirement raised was not communicated properly. Needed it for questions | 2024-01-04
Need FIB MCQ Type for the HTML, CSS, Web coding and SQL as well | Done | In the revision sets we are planning to give the multiple MCQ types, due to it is not available we are compromising here | Vijay | 4 | 0
Need Edit feature for cheet sheets | Discarded | We are having prod mistakes in cheet sheets, If we get the edit button for updating the cheetsheets, We can resolve the prod mistakes easily and quickly | Vijay |  | 1
Need search option for Question tags in admin panel | Discarded | While searching for question_tags it takes long time to get the expected question because of pagination | Swami |  | 2
Need Edit feature for both question text and options as well in Tutorials | Discarded | Updating options, question text in all types of mcqs in tutorials, it take atleast 15 - 20 Mins to update 1 MCQ option, as we are loading more number of questions, tutorials these days, It will be helpful if we get edit option | Swami |  | 1
Need feasibility to create full stack application in React IDE | Discarded | Currently in react IDE users can develop front end application, but going forward we may ask them to develop a full stack applications currently we dont have that feasibility. | Preethi |  | 1
Need a feature to move the steps from one tutorial to another tutorial and need to unlink the steps from one tutorial | In sprint | We have added more tutorial steps in interview kit as users are getting frustrated as there are number of steps we want a feature to unlink a step/ to move the step from one tutorial to another tutorial | Chanakya |  | 1 |  | 2024-01-04
Need to restric a configurator/ need to raise an error if there is any mismatch between question type and unit type Ex: Unit Type: CODING Linking 5 questions to the unit, in that 5 questions 1 question type is HTML_CODING, in this case it should throw an error like question type and Unit Type are mismatched. | Backlog | This helps us to avoid issues in prod , if there is any review mistakes / configuration mistakes are done | Swami |  | 1 | How many such cases have come actually? Aren't there SOPs to ensure this doesn't happen?
Feature: Customising the instructions in coding questions (to give company assignments in pool) | Backlog | We need a feature like IDE, where on one side we have content related to question etc.. on the other side we will have instructions. We are planning to give the company assignments as coding questions as we want to give this as a pool to the users. Instructions will be same but in few cases it differs, so it would be better if we have a cuustomized instructions feature. | Preethi |  | 2 | We can add another tab instead in coding questions in addition to existing Question, Tutorial, Discussion tabs
Script to make beta = prod | Done | Currently data in beta is not equal to prod, which is one of the blocker for us to use and text the existing content for revision, if we have beta = prod it will be also helpful for course versionings and other teams as well | Kavya |  | 1 |  | 2023-10-06
Need language selection option in code content in the DSA cheatsheets/tutorials | Done | To provide the content in all languages to users without making the cheatsheet lengthy | Priyanshi |  | 1 |  | 2023-12-06
We need to raise a feature for thumbs up and feedback for tutorial steps | Backlog | This is to understand whether the user understood the particular interview kit content | Chanakya |  | 2 | In discussion with Pavan, will finalise by 24 Nov
Updating order of tutorial steps script from product team | Backlog | As we are working on Interview Kit, we are getting data reccursively, and if we get similar questions belongs to one concept, we can arrange the order to bring effective learning | Chanakya | 2 | 2 |  | Unanswered comment
Should be able to unlink tutorial steps | Backlog | If there is any issue in configuration, there are chances to get issues in remaining steps of the tutorial. If we have this, we can delete one step where we have the issue In interview kit there can be some questions which are very closely related. It such cases we might unlink those steps | Chanakya | 1 | 2 |  | Unanswered comment
Expand button for code blocks for tutorials | Backlog | Currently we have scorll option in the cheet sheets, but we dont have in tutorials, it would be effective if we have this expand button | Chanakya | 3 | 2 |  | Nov
Need course wise feedback | Backlog | Want to get the feedbacks from users, in course level to find and improve the existing curriculum | Kavya |  | 2 |  | nov
Point : Updating mistakes in Code_Analysis questions. Whenever there is a mistake in code analysis question code, taking time to get the code_id an updating it through admin panel | Discarded | Requirement : Adding an edit feature for the Code_analysis questions code will reduce the updating time | Kamal |  | 3 | commented
Should be able to add Web Coding Questions, SQL coding questions as tutorial steps | Backlog | We dont have feasibility to create titorial for Web coding questions, we need Web coding platform itself where user can see the test cases , preview in the tutorial tab | Chanakya |  | 2 |  | nov
Point : Updating the Content in Cheat Sheet Actual Process : - Get the `learning_resource_id`. - Update the content through admin panel. | Discarded | Requirement : Adding an Edit feature for cheat sheets will reduce the time If we get content updates for 10 cheat sheets as a bulk, it takes atleast 1 hour to update it in Beta, Gamma, and Prod. Getting this feature can reduce the time upto 20 - 25 mins | Kamal |  | 3
implement the primary unit | Backlog | We have primary unit data which we have collected need to update the existing primary units accordingly and need to update all the null data in database with primary unit | Kavya |  | 2
Adding Error Checks in Admin Panel. | Backlog | Unusual Configurations Allowing Successful Loading in Admin Panel. | Kamal |  | 3 | https://docs.google.com/document/d/1LGdxH73CTRzfr6Kg-NnNOjF0bYPjv6wlFfUmnseM3DY/edit?usp=sharing
Point : Updating the child order If there are more number of units in a topic, whenever we add a new unit in between, arranging the unit IDs in a JSON format takes time. | Backlog | Requirement : Adding a drag and drop feature for the whole units. Instead of arranging the JSON format and updating though admin panel, this feature will enhance the time | Kamal |  | 3
Separate Loading Accounts for Each Curriculum. | Backlog | To enhance data management efficiency and reduce searching time | Kamal |  | 3 | This requirement is also mentioned in above doc
API of the all the mcqs related data. | Backlog |  | Vijay |  | 3
We need event to be raised inorder to track the Unit ID when user submits the form in company assignments | Discarded | This is to know to which question user is submitting the
Need a Jupyter script for updating unit names in bulk | Backlog | Updating unit names taking 4 - 5 mins per unit in beta & prod | Swami |  | 4
Need a Jupyter script for updating the short text for coding questions in bulk | Backlog | Updating short text for coding questions taking 4 - 5 mins per question in beta & prod | Swami |  | 4
Need code block expand button for MCQs For markdown content type MCQs if the code is more than 10 lines we have to scroll through the code block |  | It helps users to easily go thourgh the codes which are more then 10 lines. It is similar to the expand button code blocks in learning resources | Chanakya
The width of the code block should not be dependent on the text. For the MCQs whose content type is markdown and it has a code block in it. The width of the code block is relative to the text provided. It is not expected |  | With the current issue, in some cases only one or two keys in the code snippets are visible in the code block and for the reamining code user has to scroll | Chanakya

## Product
Requirement | Due Date | Development/Config | Status | Why | What | Priority | Timeline from Content | Delivery date | Comments
Speech to Text Content type loading | 2023-08-25 |  | Done | Improve interview performance | Abstract the existing question/answer in nxtmock in to a new content type and provide the same interview prep experience while learning in the curriculum just after each topic in the learning path. In the first roll out, 2 units of 5 questions for Programming Foundations topics | 1 | 9th September 2023 | 12th September 2023
Tutorial rearranging | 2023-08-26 |  | Done | Better user experience using step wise approach Byte sized learning Removing the user feeling of Tutorial being too lengthy | Rearrange ALLTutorials in steps | 1 | 2023-10-27
Creating hidden course for testing in Prod | 2023-09-22 |  | On hold | For testing new features and content types | Hidden course with all content types | 1 | 2023-10-27
Adding Hotspots to videos | 2023-10-30 |  | Done | Improve video understanding Not allow skipping video till end for completion | Adding hotspots to atleast 15 videos in addition to exiting Rearranging existing hotspots according to guidelines PRD and Guidelines: https://hospitable-newsprint-dcd.notion.site/PRD-Hotspots-enhancement-c91ad65cbc57444395865d215743b3dd?pvs=4 | 1 |  | 2023-10-18
Combined Exam loading for testing | 21st September 2023 |  | Done | This will ensure continuity for the user and allow us to evaluate the user more holistically using different question types | MCQ + Coding exam | 2
Changing React and Node content regarding offline IDE to online IDE | 2023-10-20 |  | Done | Rolling out online IDE to users so the existing content is misleading |  | 1
Approach roll out |  | Development | On hold | First roll out with 5 questions successful Need to check wide scale impact with 30 coding questions | Rolling approach MCQs to questions with most Tutorials seen on a weekly 5 basis | 1 | 2 more by 14-12 Next sprint target: 5 |  | On Hold since bandwidth not available
Adding Visualizer for DSA |  | Config - DSA | In sprint | Improved understanding of algorithms and increasing user engagement | Adding visualizer under relevant video sessions | 1
IDE exam | 9th September 2023 |  | Done | increase learning in IDE based topics (Spring boot, Node, React) | Loading 1 IDE exam | 2 | Oct | 2023-09-22
Making hotspots mandatory and changing the font colors according to new design |  | Config | In sprint | 1. Prevent skipping of hotspots from users so that we get a good understanding if the users are gaining knowledge from videos 2. Maintain the visibility of hotspots | Changing font colors if required and making sure hotspots are according to guidelines: https://hospitable-newsprint-dcd.notion.site/Content-loading-guidelines-Hotspots-132c3181d4294d5e80d6362a1302e7bc?pvs=4 | 1 |  |  | Hotspot details | 1. Need to get the sessions which has hotspots 2. Raising tasks to product team to add the mandatory key if there are many sessions or all sessions needs to mandate
Add IDE for the 3 new sessions | 2024-03-01 | Config | Done | New sessions loaded in React and Node courses. Hence need IDE under those sessions | Load IDE for 3 learning units (videos). Swami has the unit_ids | 1 |  |  |  | 1. Discuss with Swami
Optimizing Tutorial steps |  | Config | In sprint | Completion rate of a Tutorial is maximum when number of steps is less than or equal to 9. (70% as compared to 52%) | Making sure all Tutorials that are loaded as units have minimum 3 and maximum 9 steps | 1 |  |  |  | 1. Ask keshav and get those tutorial questions
Load Combined Exam | 2024-02-01 | Config | Done |  |  | 2
Load Tutorials for SQL coding practice |  | Development | Backlog |  |  | 1
Topic Exams: Convert assignments to Exams |  | Config | Backlog |  |  | 2
MCQ Exam Config changes |  | Config | Backlog | Changing config of MCQ exams to enable the new design according to the guidelines shared |  | 2 |  |  | share list of exam_ids
Convert SQL Cheatsheets to Tutorials |  | Config | Backlog |  |  | 2
Nxtmock questions roll out |  | Config | Backlog | Back propogate Interview prep into learning path | Start with Static, then React, then all other MERN courses | 3
Convert SQL assignments to exams |  | Config | Backlog |  | Convert SQL assignments to exams | 3
Convert all Course exams to combined exam with new MCQ unit |  | Config | Backlog |  | Convert all Course exams to combined exam with new MCQ unit | 3
Adding Code analysis and Drag and Drop in Tutorial |  | Development | Backlog | Improving the analytical and sequential thinking while learning through Tutorial Better engagement and user experience | Add the 2 new question types in existing/newly made Tutorials | 4 | 2023-11-01
Add a Tutorial on how to use VSCode in Node and React |  | Development | Backlog | Users are asking how to do personal projects or any future development work | Add a Tutorial on how to use VSCode Node and React | 4 |  |  | Check with Dinesh
Adding Coding Questions to Question Bank directly |  | Development | Backlog | Async way to practice outside the given curriculum | Preparing coding questions and load it seperately in Question Bank | 4 | 2024-01-01

## NIAT Product requirements
Requirement | Description | Status | POC | Delivery date | Remarks | Discussion | KT Document | Raised by
Targeted Learning Management | - Section-specific quiz scheduling with time restrictions Developed a user specific slot scheduling mechanism for exams. | Done | Anurag | 17/10 | KT given to Santosh kavyasri.malapaka@nxtwave.co.in Please make sure it is used as soon as possible and update if any difficulty.
Targeted Learning Management | - Instructor control over classroom quiz availability | Todo | Pratyush |  | This needs to be thought out since it will be a big tech effort. The entire role of instructors and what controls and interactions they will have with content resources needs to be well-designed.
Comprehensive Feedback Collection | - User feedback for quiz types Daily Quiz Classroom Quiz Fortnight Quiz Final Course Project Combined Exam | Done | Pratyush
Comprehensive Feedback Collection | - Question-level feedback for: Multiple Choice Questions (MCQ) | Todo | Anurag |  | Question-level feedback for: Multiple Choice Questions (MCQ) - As far as I understood, the main pain point here is that content team does not have direct visibility of any user reported errors/bugs. I think a third party bug reporting solution might be more useful rather than feedback. | Is the major reporting from student or mentors? If it's just mentors then maybe a simple google form with automated emails should do the job? |  | Pushpa (POD 3)
Enhanced Question Types | - SQL Fill-in-the-Blank (FIB) support | Done | Anurag | 2024-11-26 | We had built Web FIB for Web coding with the goal of increasing learning outcomes. But I am not sure on what actual metric level impact that had and how far we rolled it out. Hence skeptical about impact and priority here. | Other options won't have run functionality But, the impact can't be quantified directly Overall idea is that using different content types helps keep user engaged and in knowledge retention.
GPT proof content type | - New "Description with Technical Words" content type: Yet to be ideated | Todo | Pratyush |  | Ideation
Restrict direct access of Help methods for NIAT | - Tutorial unlocking tied to 50% testcase completion - When a student is stuck, while solving a coding question -> Redirecting to previously answered linked questions -> Time Gap -> Then to approach questions -> More Time Gap -> Then to tutorial -> Hence making sure most of the users solve these on their own - Removal of general Get Help feature from Coding Questions | Closed without action | Anurag | 2024-11-08 | Here, there are a lot of conflicting strategies going ahead (AI Tutor, Approach questions, etc). | Can be done in the short term for controlling how NIAT is solving coding questions Only 1.6% users have used Help before solving a coding question. Hence deprioritising for now. Can pick up later when designing the entire experience
Coding Environment | - Next.js support in Cloud IDE | In progress | Anurag | 2024-12-13 | In beta. Content team loading NextJS question for testing.
Coding Environment | -Tailwind CSS support in Code playground | Done | Anurag | 2024-10-30 | Can be directly used with CDN method. Disabling in line errors
Coding Environment | - Flex Box Froggy integration for responsive web design training | Content action req | Debjyoti |  | POC can be done with direct link sharing, then can be integrated in platform | Will do after POC
AI-Enhanced Learning | - O1 preview model for generating programming foundations course approach questions | Done | Anurag |  | Here, there are a lot of conflicting strategies going ahead (AI Tutor, Approach questions, etc). | Try o1 preview for AI tutor with different prompts based on user situation Checked. Cost will shoot up by 7x. Also current model giving good results.
Timer for each MCQ Question | To eliminate the MalPractice in Daily Quiz | Backlog |  |  | High effort and possibly not the best approach as users might take different time with different questions. Suggestion: Load multiple sections with slots and durations containing 5-10 mcqs each" | Mentee like approach can also work maybe Think more about Instructor led blended learning experience |  | Preethi (POD 1)
Personalization of revision questions | Personalize revision questions for each student based on their classroom quiz, daily quiz attempts. | In progress | Anurag | 2024-12-27 | High effort, need to validate Maybe can combine with the daily revision effort
sequential attempts in coding practice sets | Tailor the user experience to mandate sequential attempts in coding practice sets. This ensures students build skills progressively and don't skip foundational questions. | Backlog |  |  | High effort, need to validate
explanations for incorrect MCQ answers | In practice sets, implement pop-up explanations for incorrect MCQ answers, including code analysis MCQs. This should appear immediately after a wrong submission to reinforce learning. | Content action req | Debjyoti |  | Explanations already present as a feature. Is there any UI difficulty that we are facing? | Explanations behaviour checking
planning phase of coding questions | Develop product features to encourage planning before coding. Consider implementing a "planning phase" before allowing code input. | Backlog | Pratyush
Content types/Features that will be GPT proof and evaluate whether the user has used AI to solve or applied his/her own understanding | Create a new content type where a code snippet is given in lines, and the question asks to explain how a specific line works. | Todo | Anurag |  | Not clear How is this different from code analysis? | Want to check if user understood the code or not Basically solving for GPT generated solutions Check if AI Tutor can serve this purpose. By asking after correct solving on the details of solving the code |  | Chanakya (POD 3)
SQL Visualiser | Ref: https://www.instagram.com/reel/C_0gjzRSWQ5/?igsh=NzA2bW9jdjRxZHBl | Todo | Pratyush |  | What is the problem statement here? | Check if a hardcoded solution is doable just as an instructor tool |  | Chanakya (POD 3)
Random Allocation of Course Projects | Problem Statement: We want to deliver 1000 Projects to NIAT Students, have created the content. Can we think about the delivery of this, such that each user should get only one. Randomly allocated. Note here displaying 1000 units in one course itself may lead to UI/UX issues - Getting struck etc Also we dont want to display all the projects to all users -> Each user should be able to see his own allocated project | Closed without action
Bulk test case updates using Jupiter Scripts | We need Jupiter scripts to update test cases. Specifically, we require scripts for the following updates: * Bulk test case criteria * Bulk test case type ( Already developed, it needs to be provided to us as a Jupiter script ) * Bulk test case scores * Bulk test case display texts Note: We need these scripts for Web Coding questions, FIB Web Coding (HTML and Python), and Coding Questions (Python, JavaScript, etc.). | Done | Ritesh | 2024-12-12 |  |  |  | Vijay (POD 4)
Adding support for Node.js v20 in Cloud IDE | Adding support for Node.js v20 in Cloud IDE ensuring seamless compatibility with updated react-router v7 | In progress | Ritesh |  |  |  |  | Pushpa (POD 3)
Add update feature for function based testing | Currently we are not having any module for updating the function based testing test cases, we need a module expecting in the admin panel | In progress | Ritesh | 2024-12-19 |  |  |  | Vijay (POD 4)
We need to assign 104 cheat sheet projects to individual students within a unit. | Need to develop user-specific content for cheat sheet projects. Requirements: 1) Total 104 unique cheat sheet projects 2) Must be distributed among 1200 students 3) Each student gets exactly one project 4) Distribution should be section-wise 5) Assignment should be random within sections. | Done | Rajesh | 2024-12-30 |  | We will provide details on project assigning for each student and require flexibility to load user-specific content in the unit. |  | Pranathi(POD 3)
Access of these Model on Gamma and Prod: 1. Home › Nkb_Question › Question testcases 2. Home › Nkb_Coding_Core › Test case detailss | We need to update the test case details of the Python coding question for that want the below access on Gamma and Prod admin panel: Home › Nkb_Question › Question testcases Home › Nkb_Coding_Core › Test case detailss Or else we can ask for Prod Jupyter script credentials to do the same. | In progress | Ritesh |  |  |  |  | Vishal (POD 4)
add pre-filled code in Beta, Gamma, and prod for NIAT Responsive Course, in one question. | Add the script tag for the font awesome icons in the pre filled code for NIAT RESPONSIVE COURSE quiz coding questions with the tag name of RESPONSIVE_WEBSITE_1 and update in beta, gamma, prod the script tag tp be added in the pre filled code is as follows <script src="https://kit.fontawesome.com/fac54f0bd8.js" crossorigin="anonymous"></script> | In progress | Ritesh |  |  |  |  | Khushi (POD 4)
experiencing issues with PUPPETEER_BASED test cases in the beta and gamma portal. | We are experiencing issues with PUPPETEER_BASED test cases in the beta and gamma portal. Priority: High Below are the IDs and failed images for reference. Gamma ID:- https://learning-gamma.ccbp.in/question/07bb5143-7221-4a97-a5b4-a11ee02e8c7a Beta ID:- https://learning-beta.earlywave.in/question/07bb5143-7221-4a97-a5b4-a11ee02e8c7a Please resolve this as soon as possible, as it will affect the review process.
Providing support for React vite project | context: Previously we used CRA to create a react app, as its depricated, we are planning to switch to vite and explain about vite to students as well. I tried running the vite project in cloud IDE. Not able to see the output Testing Link: https://learning-beta.earlywave.in/ide/RJSCPBGC7K?d=1&e_t=VU5JVA==&s_id=3a1558c5-8133-4c66-b036-dc8e21725dc7&e_w_i=true&r_v=true Note: This will be the blocker for React course planning and execution. Which is planned to deliver ASAP | In progress | Ritesh
Model access on Beta, Gamma, and Prod environments for 'fibsql coding'. for 'content_loader' user | Purpose: To get the Code block Id from admin panel , that id is requred to Update FIB SQL Questions code blocks When We got Prod Mistakes in that
online ide feature is not supported in gamma. | Impact : we have to load the same content in beta to check if loaded correctly or not instead of directly checking from the gamma. | Backlog | Anurag | May-June | Added in backlog. Since these aren't high impact changes, will be picked when there is extra bandwidth. From student learning outcomes point of view, streamlining content team workflow would be lesser impact than delivering user facing features. |  |  | POD 4
There is no feature to open multiple online ides at a time from the same account . | At a time from one account only one ide can be opened , there is no feature to open multiple ides at a time from the same account . Impact: we have to close one in order to open another from the same account . it's acceptable to keep it for internal team members only, since this feature might only be needed by developers/testers. | Backlog | Anurag | May-June | Added in backlog. Since these aren't high impact changes, will be picked when there is extra bandwidth. From student learning outcomes point of view, streamlining content team workflow would be lesser impact than delivering user facing features. |  |  | POD 4
React code editor feature | We recently added a React code editor feature to the Reading Materials: https://link2past.github.io/sandpack-react-code-block/ We will create a new course, "Testing Frontend Applications," and it requires a "Run Tests" button to execute the test cases. When we click on the Run Tests button, the test cases should get executed: https://codesandbox.io/p/sandbox/unit-testing-practice-h2kqm | In progress | Ritesh |  |  |  |  | POD 4
MySQL Code playground | We are going to add MySQL course to the curriculum based on the companies feedbacks User should be able to write MySQL queries on a database and should see the results of the execution User should be able to run advanced concept queries related to stored procedures, triggers, |  |  | Aug-Sept |  |  |  | Chanakya
Django IDE | We are going to add MySQL course to the curriculum based on the companies feedbacks User should be able to create projects Link the created projects to React Applications |  |  | Sept-Oct |  |  |  | Chanakya
Teach Back Feature | Located below each lesson, students answer AI generated questions related to the current lecture via microphone. Responses are transcribed and evaluated by AI. A score is assigned based on answer accuracy. If the score meets the threshold, the chapter is marked complete. If not, the student must rewatch the session and try again. |  |  | 22nd July |  |  |  | Chanakya
Support Python code execution (including package installation, etc.) Should be available under Session, Practice, and Exam modes Features to include: Prefilled code for all modes (Session, Practice, Exam) Save and Reset options Submit functionality with test cases integration | We’re teaching a “Building LLM Applications” course to students, where we cover topics like integrating LLMs in Python through APIs, building applications using LangChain, developing RAG applications, and deploying them using Gradio and Hugging Face. | [6 empty] | Pushpa
HTML-Based Interactive Tutorials | Current Limitation Our learning portal currently supports only Markdown rendering and does not have the capability to render or display HTML content. This creates a gap between: The desired tutorial experience (HTML-based interactive content) The platform's current rendering capabilities (Markdown only) Product Inspiration We are looking for an experience similar to the way the ChapterPal platform presents research papers and educational content. Instead of exposing the complete content at once, ChapterPal: Breaks information into smaller, digestible sections Reveals content progressively Encourages active learning through interactions Guides learners through a structured reading journey rather than displaying a static document Proposed Requirement We need a product feature that enables: HTML-based tutorial generation and rendering. Progressive disclosure of content (section-by-section learning). Interactive learning experiences instead of static reading materials. A ChapterPal-like content presentation model where learners consume content in guided steps rather than viewing the entire material at once. |  | Narayani Lokeshwar Reddy | 22nd June

## GenAI<>Prod
Course | Requirement | Priority | Status | Tentative Timeline | Remarks | Prod Team Comments Include date whenever new comment has been added) | Content Team Comments (Include date whenever new comment has been added)
Intro to Generative AI | n8n version update (memory mistral node) | P1 | Completed | In beta - 3rd April (Friday) In prod - 6th April (Monday) | - | 22 April Done | Tested all others previously (including Gemini), but dedcied Mistral is the suitable one since w.r.t the student perspective as well, they would explore this newly
Building LLM Applications | IDE launching time optimization | P2 | Completed | This would be completed next week only. as Backend devs were mostly busy with training and some were on leave. | Current IDE launch time is 6 - 6.5 min, aim to reduce it to 2-3 mins | 22 April The launchtime has been optimised to approx 3 mins. Task is in deployment stage
Building LLM Applications | Session code playground for building LLM Applications | P4 | Yet to pick |  | Currently we are using google colab for teaching Building LLM Applications course. We can have an IDE just below the video session similar to React, Node JS, etc | 22 April We have given coding practice of LLM, it just needs to be loaded under video session.
Building LLM Applications | Improved AI Evaluation | P5 | Yet to pick |  | Prompt enhancement | 22 April As i was informed, only the last test case was hallucinating in AI Evaluations, which has been fixed thorugh .eval ignore task. So this task is not needed.
Building LLM Applications | IDE exam feature | - | In-progress | Chandravamsi needs to finish testing | In Progress | 22 April Devleopment done. But need to release to users. Blocked due to pending testing of .eval ignore.
Building LLM Applications | .evalignore issue (If files are not included in .gitignore, the AI hallucinating) | P1 | In-progress |  |  | 22 April Testing is pending from genAI team. | We can proceed with this approach. Once testing is completed from your end, kindly confirm if everything is working as expected. Based on your confirmation, we will proceed with the approach from our end.
Sem-3, Practical Software Engineering, AI Full-Stack Projects | Full Stack IDE | P3 | In-progress |  | Similar to react IDE, integration requried between both front end and back end | 22 April This task is in progress. Currently we have VS Code IDE which can run two backend and frontend ports both, but do not have preview tab. So, devs are working on this task.
Sem-3 AI For finance | Package Installation IDE - Data Science | p0 | Pending |  | Add the following packages to Cloud IDE: finnhub-python==2.4.270 (0.12 MiB) jsonref==1.1.0 (0.05 MiB) fairlearn>=0.9.0 aif360>=0.5.0 shap>=0.43.0 lime>=0.2.0 alibi>=0.9.0 interpret>=0.4.0 | 22 April You can directly add them requirement.txt while loading the question in a particular session.
Sem-3 AI For finance | checking fesability in our ide for teaching the fine tuning | p0 | Pending |  | Add the following packages to IDE: unsloth (latest) unsloth_zoo (latest) transformers>=4.36.0 datasets>=2.16.0 peft>=0.7.0 trl>=0.7.0 bitsandbytes>=0.41.0 accelerate>=0.25.0 xformers (latest) torch>=2.1.0 (with CUDA support) huggingface_hub>=0.19.0 sentencepiece>=0.1.99 protobuf>=3.20.0 evaluate>=0.4.0 tensorboard>=2.15.0 Estimated Total Size: ~12-15 GiB CRITICAL REQUIREMENTS VERIFICATION NEEDED: 1. Does the IDE have GPU access? (Minimum 8GB VRAM - T4/V100/A100) 2. Is CUDA installed? (Version 11.8+ or 12.x required) 3. Available disk space? (Minimum 20GB needed) 4. RAM allocation per session? (Minimum 16GB recommended) 5. Can packages requiring C++ compilation be installed? (bitsandbytes, xformers) 6. Session timeout limits? (Fine-tuning can take 30-60 minutes) NOTE: Without GPU support, fine-tuning hands-on training will not be feasible. | 22 April Would set up a meeting with devs regarding this.
Sem-3, Practical Software Engineering, AI Full-Stack Projects | Full Stack IDE with ai integration (similar to cursor) | p0 | Pending |  | Request raised to demonstrate how real-world projects are currently being built using AI-assisted development tools. Students need hands-on experience with AI-integrated IDEs to understand modern software development practices. This will teach practical workflows including: AI-assisted coding, prompt engineering for code generation, debugging with AI, refactoring legacy code, generating tests and documentation, | 22 April As we are already working on Full Stack IDE for genAI team, after that is done, we will see the possibility of adding an Ai Agent in VS Code IDE. Will discuss with devs.
Building LLM Applications | need alternative Beta Account for Gen AI, for testing | p1 |  |  | Requesting an alternative Beta account for our course. Currently, both the Tech team and Product team are using the same account, which is leading to a few challenges: When two users open the IDE at the same time, it gets relaunched, which blocks testing and requires waiting until one user completes their session. In some cases, required packages are not getting installed during testing. If one tester installs them manually, the issue does not appear for others, which creates confusion in identifying the actual problem. Having a separate account would help reduce testing time and provide better clarity on feature behavior.
Introduction to Gen AI | need HTML-Based Interactive Tutorials rendering and A ChapterPal-like content presentation model where learners consume content in guided steps rather than viewing the entire material at once. |  |  |  | Current Limitation Our learning portal currently supports only Markdown rendering and does not have the capability to render or display HTML content. This creates a gap between: The desired tutorial experience (HTML-based interactive content) The platform's current rendering capabilities (Markdown only) Product Inspiration We are looking for an experience similar to the way the ChapterPal platform presents research papers and educational content. Instead of exposing the complete content at once, ChapterPal: Breaks information into smaller, digestible sections Reveals content progressively Encourages active learning through interactions Guides learners through a structured reading journey rather than displaying a static document Proposed Requirement We need a product feature that enables: HTML-based tutorial generation and rendering. Progressive disclosure of content (section-by-section learning). Interactive learning experiences instead of static reading materials. A ChapterPal-like content presentation model where learners consume content in guided steps rather than viewing the entire material at once.

## GenAI Prod Issues
Date | Content Team POC | Issue Type | Issue Description | Issue Status | Product Team POC | Reference Links/Docs | Remarks (mention date whenever new info has been added)
The Import button in the HTTP request node is not working.
LinkedIn Node in n8n has an issue
Simple memory node
History component

## Prioritization Guidelines
Urgency | Needed in
1 | Next quarter
2 | Next month
3 | In 2 weeks
4 | Next week
5 | Now
Impact
0.25 | No learning or outcome metrics moved
0.5 | Minor metric movement
1 | Better learning experience, noticeable metric change
2 | High impact, makes learning a lot easier and gives direct outcome
3 | Extremely high impact, revolutionizes learning
Effort | How many weeks to do it
1 | Within the same sprint
2 | 1 entire sprint
3 | May flow to 2 sprints
4 | 3-4 sprints
5 | More than a month